## Sample Risk List
Please note: This list is only a sample of potential risks a project may be exposed to. And should only be used by the Project Team as areference and starting point for risk identification and analysis on a particular project.
Environmental Risks | External Risks | Design Risks | Engineering Services Risks | Right of Way Risks | Construction Risks | Project Management Risks | Organizational Risks
Environmental analysis incomplete | Landowners unwilling to sell | Design incomplete | Foundations utilizing Cast-In-Drilled-Hole or Cast-In-Steel-Shell pile 30” in diameter or greater may require tunneling and mining provisions within the contract documents and early notification of Cal-OSHA | Utility relocation requires more time than planned | Inaccurate contract time estimates | Project purpose and need is not well-defined | Inexperienced staff assigned
Availability of project data and mapping at the beginning of the environmental study is insufficient | Local communities pose objections | Unexpected geotechnical or groundwater issues | Bridges constructed at grade and then excavated underneath may require tunneling and mining provisions within the contract documents and early notification of Cal-OSHA | Unforeseen railroad involvement | Permit work window time is insufficient | Project scope definition is incomplete | Losing critical staff at crucial point of the project
New information after Environmental Document is completed may require re-evaluation or a new document (i.e. utility relocation beyond document coverage) | Unreasonably high expectations from stakeholders | Inaccurate assumptions on technical issues in planning stage | Hazardous materials in existing structure or surrounding soil; lead paint, contaminated soil, asbestos pipe, asbestos bearings and shims | Resolving objections to Right of Way appraisal takes more time and/or money | Change requests due to differing site conditions | Project scope, schedule, objectives, cost, and deliverables are not clearly defined or understood | Insufficient time to plan
New alternatives required to avoid, mitigate or minimize impact | Political factors or support for project changes | Surveys incomplete | Piles driven into fish habitat may require special noise attenuation to protect marine species | Right of Way datasheet incomplete or underestimated | Temporary excavation and shoring system design is not adequate | No control over staff priorities | Unanticipated project manager workload
Acquisition, creation or restoration of on or off-site mitigation | Stakeholders request late changes | Changes to materials/geotechnical/foundation | Special railroad requirements are necessary including an extensive geotechnical report for temporary shoring system adjacent to tracks | Need for “Permits to Enter” not considered in project schedule development | Falsework design is not adequate | Consultant or contractor delays | Internal “red tape” causes delay getting approvals, decisions
Environmental clearance for staging or borrow sites required | New stakeholders emerge and request changes | Bridge site data incomplete to DES | Access to adjacent properties is necessary to resolve constructability requirements | Condemnation process takes longer than anticipated | Unidentified utilities | Estimating and/or scheduling errors | Functional units not available, overloaded
Historic site, endangered species, riparian areas, wetlands and/or public park present | Threat of lawsuits | Hazardous waste site analysis incomplete | Existing structures planned for modification not evaluated for seismic retrofit, scour potential and structural capacity | Acquisition of parcels controlled by a State or Federal Agency may take longer than anticipated | Buried man-made objects/unidentified hazardous waste | Unplanned work that must be accommodated | Lack of understanding of complex internal funding procedures
Design changes require additional Environmental analysis | Increase in material cost due to market forces | Unforeseen design exceptions required | Foundation and geotechnical tasks (foundation drilling and material testing) not identified and included in project workplan | Discovery of hazardous waste in the right of way phase | Dewatering is required due to change in water table | Lack of coordination/communication | Priorities change on existing program
Unforeseen formal NEPA/404 consultation is required | Water quality regulations change | Consultant design not up to Department standards | Bridge is a habitat to bats or other species requiring mitigation or seasonal construction | Seasonal requirements during utility relocation | Temporary construction easements expire | Underestimated support resources or overly optimistic delivery schedule | Inconsistent cost, time, scope and quality objectives
Unforeseen formal Section 7 consultation is required | New permits or additional information required | Unresolved constructability items | Condition of the bridge deck unknown | Utility company workload, financial condition or timeline | Electrical power lines not seen and in conflict with construction | Scope creep | Overlapping of one or more project limits, scope of work or schedule
Unexpected Section 106 issues expected | Reviewing agency requires longer than expected review time | Complex hydraulic features | For projects involving bridge removal, bridge carries traffic during staging | Expired temporary construction easements | Street or ramp closures not coordinated with local community | Unresolved project conflicts not escalated in a timely manner | Funding changes for fiscal year
Unexpected Native American concerns | Changes to storm-water requirements | Unable to meet Americans with Disabilities Act requirements | Verify that all seasonal constraints and permitting requirements are identified and incorporated in the project schedule | Inadequate pool of expert witnesses or qualified appraisers | Insufficient or limited construction or staging areas | Unanticipated escalation in right of way values or construction cost | Lack of specialized staff (biology, anthropology, geotechnical, archeology, etc.)
Unforeseen Section 4(f) resources affected | Permits or agency actions delayed or take longer than expected | Project in a critical water shortage area and a water source agreement required | Complex structures hydraulic design requiring investigation and planning |  | Changes during construction require additional coordination with resource agencies | Delay in earlier project phases jeopardizes ability to meet programmed delivery commitment | Capital funding unavailable for right of way or construction
Project may encroach into the Coastal Zone | New information required for permits | Incomplete quantity estimates | Assumptions upon which the Advance Planning Study is based on are realistic and verification of these assumptions prior to completion of the Project Report |  | Late discovery of aerially deposited lead | Added workload or time requirements because of new direction, policy, or statute
Project may encroach onto a Scenic Highway | Environmental regulations change | Unforeseen construction window and/or rainy season requirements | Design changes to alignment, profile, typical cross section, stage construction between Advance Planning Study and the Bridge Site Submittal |  | Experimental or research features incorporated | Local agency support not attained
Project may encroach to a Wild and Scenic River | Controversy on environmental grounds expected | New or revised design standard | Unexpected environmental constraints that impact bridge construction |  | Unexpected paleontology findings | Public awareness/campaign not planned
Unanticipated noise impacts | Pressure to deliver project on an accelerated schedule |  | Unforeseen aesthetic requirements |  | Delay in demolition due to sensitive habitat requirements or other reasons | Unforeseen agreements required
Project causes an unanticipated barrier to wildlife | Labor shortage or strike |  | Delay due to permits or agreements, from Federal, State, or local agencies for geotechnical subsurface exploration |  | Long lead time for utilities caused by design and manufacture of special components (steel towers or special pipe) | Priorities change on existing program
Project may encroach into a floodplain or a regulatory floodway | Construction or pile driving noise and vibration impacting adjacent businesses or residents |  | Delay due to Right-of-Entry agreements for geotechnical subsurface exploration |  |  | Inconsistent cost, time, scope, and quality objectives
Project does not conform to the state implementation plan for air quality at the program and plan level |  |  | Delay due to traffic management and lane closure for geotechnical subsurface exploration
Unanticipated cumulative impact issues