## Sheet1
| High Risk Category | If yes score = 5 | Medium Risk Category | If yes score = 3 | Low Risk Category | If yes score = 1 | No risk Category | If yes score = 0 | Sum for all Questions | Total Risk levels
Budget Risk | [9 empty] | 0 = No risk 1-8 = Low Risk 9-17 = Medium Risk 18-25 = High Risk
What is the estimated total project cost? | Project cost is greater than $5 million. | 0 | Project cost is greater than or equal to $1 million and less than or equal to $5 million. | 0 | Project cost is greater than or equal to $100 thousand and less than $1 million. | 0 | Project cost is less than $100 thousand. | 0
What percentage of the agency budget does the project represent? | The project is 15% or more of the agency budget. | 0 | The project is greater than or equal to 5% and less than 15% of the agency budget. | 0 | The project is greater than or equal to 2% but less than 5% of the agency budget. | 0 | The project is less than 2% of the agency budget. | 0
Have sufficient project funds been budgeted and allocated? | Funding is not budgeted or allocated. | 0 | Funding is available but not allocated. | 0 | Minimum essential funding is budgeted and allocated. | 0 | All funding is budgeted and allocated. | 0
How much confidence is there in the expenditure and funding projections? | Accuracy of budget estimate is less than or equal to 50%. | 0 | Accuracy of budget estimate is greater than 50% and less than or equal to 85%. | 0 | Accuracy of budget estimate is greater than 85% and less than or equal to 95%. | 0 | Accuracy of budget estimate is greater than 95% and less than or equal to 100%. | 0
Is funding available for maintenance of the project deliverable after project closure? | Maintenance funding has not been planned. | 0 | Maintenance funding is planned but constrained. | 0 | Maintenance funding is planned and available. | 0 | Maintenance funding is available. | 0
Total Score-Budget Risk | [8 empty] | 0
External Dependencies Risk | [9 empty] | 0 = No risk 1-5 = Low Risk 6-10 = Medium Risk 11-15 = High Risk
Is this project dependent on another projects deliverable? | A project deliverable from another project is required. | 0 | The project will utilize other project deliverables. | 0 | Other deliverables enhance the project. | 0 | No other deliverables are required. | 0
Does this project require resources from other organizations? | External resources are critical to the project. | 0 | Project requires some external resources. | 0 | Project requires few external resources. | 0 | Project requires no external resources. | 0
Does this project require data from other sources? | Data from other sources has a significant impact. | 0 | Data from other sources has some impact. | 0 | Data from other sources has little impact. | 0 | No other data is required. | 0
Total Score-External Dependencies Risk | [8 empty] | 0
Management Risk | [9 empty] | 0 = No risk 1-5 = Low Risk 6-10 = Medium Risk 11-15 = High Risk
What is the level of management commitment? | Management is not committed. | 0 | Management has demonstrated interest. | 0 | Management is committed to the project. | 0 | Management has made the project a priority. | 0
Is the project sponsor resourcing the project? | The project sponsor has control of some of the resources needed. | 0 | Project sponsor has control of most of the resources needed. | 0 | The project sponsor owns most of the resources needed. | 0 | The project sponsor owns all the resources needed. | 0
What is the experience and training level of agency project managers? | The agency has no project managers. | 0 | The agency project managers have some training or experience. | 0 | The agency project managers have training and experience. | 0 | The agency project managers are well trained and very experienced. | 0
Total Score-Management Risk | [8 empty] | 0
Mission Critical Risk | [9 empty] | 0 = No risk 1-5 = Low Risk 6-10 = Medium Risk 11-15 = High Risk
How important is the project to meeting Commonwealth Strategic Objectives? | The project is critical to meeting Commonwealth Strategic Objectives. | 0 | The project is important to meeting Commonwealth Strategic Objectives. | 0 | The project has some impact on Commonwealth Strategic Objectives. | 0 | The project has little or no direct impact on Commonwealth Strategic Objectives. | 0
How important is the project to meeting externally generated mandates? (Legislative, Executive. or Judicial) | The project is critical to accomplishment of external mandates. | 0 | The project is important to the accomplishment of external mandates. | 0 | The project enhances accomplishment of external mandates. | 0 | The project has little or no direct impact on accomplishment of external mandates. | 0
How important is the project deliverable to agency core business activities? | The project is critical to the organization core business activities. | 0 | The project is important to the organization core business activities. | 0 | The project enhances organization core business activities. | 0 | The project is has little or no direct impact on current core business activities. | 0
Total Score-Mission Critical Risk | [8 empty] | 0
Failure Risk | [9 empty] | 0 = No risk 1-5 = Low Risk 6-10 = Medium Risk 11-15 = High Risk
Has the agency and/or vendor executed similar projects? | Neither the agency nor the vendor has executed a similar project. | 0 | Agency or vendor have executed a similar project. | 0 | Agency or vendor have executed several similar projects. | 0 | Agency and vendor have executed many similar projects successfully. | 0
How will failure of the project impact the customers? | Impact of project failure on customers is high. | 0 | Impact of project failure on customers is moderate. | 0 | Impact of project failure on customers is minimal. | 0 | There is no impact of project failure on the customers. | 0
How politically sensitive is the project? | The project is very sensitive to political climate. | 0 | The project is sensitive to political climate. | 0 | Political climate has very little impact on the project. | 0 | Political climate has no impact on the project. | 0
Total Score-Failure Risk | [8 empty] | 0
Complexity Risk | [9 empty] | 0 = No risk 1-35 Low Risk 36-72= Medium Risk Greater than 72 = High Risk
How new is the technological solution? | The technology is in development (Leading Edge). | 0 | The technology has been developed but is very new. | 0 | The technology has been available for several years. | 0 | The technology is proven and has been available for a number of years. | 0
Is the application of this solution new, proven, or untried? | A new application of the technology which has never been tried before. | 0 | A new application of the technology that has been tried but is not proven. | 0 | An application of the technology has been tried and is partially proven. | 0 | Application of the technology is tried and proven. | 0
How many processes or business activities are impacted? | A large portion of the business processes are impacted. | 0 | Critical business processes are impacted. | 0 | No critical business processes are impacted. | 0 | No business process is impacted. | 0
Total Score-Complexity Risk | [8 empty] | 0
Total Risk Score for Project | [8 empty] | 0

## Sheet2
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15