## Level 1 Risk Register
LEVEL 1 - RISK REGISTER |  |  |  | Project Name: | Example Project |  | DIST- EA | 08-1234 | Project Manager | PM Person
Risk Identification | [6 empty] | Risk Rating |  | Risk Response
Status | ID # | Type | Category | Title | Risk Statement | Current status/assumptions | Priority Rating | Rationale for Rating | Strategy | Response Actions | Risk Owner | Updated
Active |  | Opportunity | Organizational |  |  |  | Very High |  | Mitigate
Dormant |  | Threat | Organizational |  |  |  | High |  | Transfer
Retired |  | Threat | Organizational |  |  |  | Moderate |  | Transfer
Low
Very Low
Active | 160 | Threat | Design | Survey File | Inaccuracies or incomplete information in the survey file could lead to rework of the design. |  | Medium |  | Mitigate | Verify that the survey file is accurate and complete | Sam Owner | 2012-10-12
Active | 161 | Threat | Environmental | Challenge to EIR | Potential lawsuits may challenge the environmental report, delaying the start of construction or threatening loss of funding. |  | Low |  | Mitigate | Address concerns of stakeholders and public during environmental process | EIR Person | 2012-11-23
Active | 162 | Threat | R/W | Delay of R/W Acquisition | Due to the large number of parcels and businesses, may have to use the condemnation process to acquire R/W, which could delay start of construction by up to one year, increasing construction costs and extend the time for COS. |  | High |  | Accept |  | R/W Person | 2012-11-23
Active | 163 | Threat | Construction | Buried Objects | Unanticipated buried man-made objects uncovered during construction require removal and disposal resulting in additional costs. |  | Medium |  | Accept | Include a Supplemental Work item to cover this risk. | PM | 2012-11-24
Active | 164 | Threat | Design | Supplemental EIR | A design change that is outside of the parameters contemplated in the Environmental Document triggers a supplemental EIR which causes a delay due to the public comment period. |  | Low |  | Avoid | Monitor design changes against ED to avoid reassessment of ED unless the opportunity outweighs the threat | Design Manager | 2012-11-24
Active | 165 | Threat | Environmental | Nesting birds | Nesting birds, protected from harassment under the Migratory Bird Treaty Act, may delay construction during the nesting season. |  | Low |  | Mitigate | Schedule contract work to avoid the nesting season or remove nesting habitat before starting work. | PM/RE | 2012-11-24
Active | 166 | Threat | R/W | Additional R/W | Due to the complex nature of the staging, additional right of way or construction easements may be required to complete the work as contemplated, resulting in additional cost to the project. |  | Low |  | Mitigate | Re-sequence the work to enable R/W Certification | R/W Person | 2012-11-24
Active | 167 | Threat | Construction | Hazardous Materials | Hazardous materials encountered during construction will require an on-site storage area and potential additional costs to dispose |  | Medium |  | Accept | Ensure storage space will be available | PM | 2012-11-24

## Level 2 Risk Register
LEVEL 2 - RISK REGISTER |  |  |  | Project Name: | Example Project |  | DIST- EA | 08-1234 | Project Manager | PM Person
Risk Identification | [6 empty] | Risk Assessment | [5 empty] | Risk Response
Status | ID # | Type | Category | Title | Risk Statement | Current status/assumptions | Probability | Cost Impact | Cost Score | Time Impact | Time Score | Rationale | Strategy | Response Actions | Risk Owner | Updated
Active | 160 | Threat | Design | Survey File | Inaccuracies or incomplete information in the survey file could lead to rework of the design. |  | 3-Moderate | 2 -Low | 6 | 4 -Moderate | 12 |  | Mitigate | Verify that the survey file is accurate and complete | Sam Owner | 2012-10-12
Active | 161 | Threat | Environmental | Challenge to EIR | Potential lawsuits may challenge the environmental report, delaying the start of construction or threatening loss of funding. |  | 1-Very Low | 4 -Moderate | 4 | 8 -High | 8 |  | Mitigate | Address concerns of stakeholders and public during environmental process | EIR Person | 2012-11-23
Active | 162 | Threat | R/W | Delay of R/W Acquisition | Due to the large number of parcels and businesses, may have to use the condemnation process to acquire R/W, which could delay start of construction by up to one year, increasing construction costs and extend the time for COS. |  | 3-Moderate | 4 -Moderate | 12 | 8 -High | 24 |  | Accept |  | R/W Person | 2012-11-23
Active | 163 | Threat | Construction | Buried Objects | Unanticipated buried man-made objects uncovered during construction require removal and disposal resulting in additional costs. |  | 3-Moderate | 4 -Moderate | 12 | 4 -Moderate | 12 |  | Accept | Include a Supplemental Work item to cover this risk. | PM | 2012-11-24
Active | 164 | Threat | Design | Supplemental EIR | A design change that is outside of the parameters contemplated in the Environmental Document triggers a supplemental EIR which causes a delay due to the public comment period. |  | 3-Moderate | 4 -Moderate | 12 | 8 -High | 24 |  | Avoid | Monitor design changes against ED to avoid reassessment of ED unless the opportunity outweighs the threat | Design Manager | 2012-11-24
Active | 165 | Threat | Environmental | Nesting birds | Nesting birds, protected from harassment under the Migratory Bird Treaty Act, may delay construction during the nesting season. |  | 2-Low | 2 -Low | 4 | 8 -High | 16 |  | Mitigate | Schedule contract work to avoid the nesting season or remove nesting habitat before starting work. | PM/RE | 2012-11-24
Active | 166 | Threat | R/W | Additional R/W | Due to the complex nature of the staging, additional right of way or construction easements may be required to complete the work as contemplated, resulting in additional cost to the project. |  | 3-Moderate | 8 -High | 24 | 8 -High | 24 |  | Mitigate | Re-sequence the work to enable R/W Certification | R/W Person | 2012-11-24
Active | 167 | Threat | Construction | Hazardous Materials | Hazardous materials encountered during construction will require an on-site storage area and potential additional costs to dispose |  | 2-Low | 2 -Low | 4 | 1 -Very Low | 2 |  | Accept | Ensure storage space will be available | PM | 2012-11-24

## Level 3 Risk Register
LEVEL 3 - RISK REGISTER |  |  | Project Name: | Example Project |  | DIST- EA |  | 08-1234 | Project Manager | PM Person
Risk Assessment
Risk Identification | [5 empty] | Probability |  | Cost Impact ($) |  |  |  | Time Impact (days) |  |  |  | Rationale | Risk Response
Status | ID # | Category | Title | Risk Statement | Current status/assumptions | Low | High | Low | Most likely | High | Probable | Low | Most likely | High | Probable |  | Strategy | Response Actions | Risk Owner | Updated
Active | 160 | Design | Survey File | Inaccuracies or incomplete information in the survey file could lead to rework of the design. |  | 40 | 60 | 100000 |  | 300000 | 100000 | [5 empty] | Mitigate | Verify that the survey file is accurate and complete | Sam Owner | 2012-10-12
Active | 161 | Environmental | Challenge to EIR | Potential lawsuits may challenge the environmental report, delaying the start of construction or threatening loss of funding. |  | 0 | 10 | 500000 | 800000 | 1200000 | 42000 | 60 |  | 150 | 5.25 |  | Mitigate | Address concerns of stakeholders and public during environmental process | EIR Person | 2012-11-23
Active | 162 | R/W | Delay of R/W Acquisition | Due to the large number of parcels and businesses, may have to use the condemnation process to acquire R/W, which could delay start of construction by up to one year, increasing construction costs and extend the time for COS. |  | 40 | 60 | 500000 | 750000 | 2000000 | 542000 | 180 |  | 365 | 136.25 |  | Accept |  | R/W Person | 2012-11-23
Active | 163 | Construction | Buried Objects | Unanticipated buried man-made objects uncovered during construction require removal and disposal resulting in additional costs. |  | 20 | 40 | 200000 |  | 400000 | 90000 | [5 empty] | Accept | Include a Supplemental Work item to cover this risk. | PM | 2012-11-24
Active | 164 | Design | Supplemental EIR | A design change that is outside of the parameters contemplated in the Environmental Document triggers a supplemental EIR which causes a delay due to the public comment period. |  | 10 | 30 | 100000 | 200000 | 400000 | 47000 | 0 |  | 60 | 6 |  | Avoid | Monitor design changes against ED to avoid reassessment of ED unless the opportunity outweighs the threat | Design Manager | 2012-11-24
Active | 165 | Environmental | Nesting birds | Nesting birds, protected from harassment under the Migratory Bird Treaty Act, may delay construction during the nesting season. |  | 0 | 20 | 150000 |  | 300000 | 23000 | 0 |  | 30 | 1.5 |  | Mitigate | Schedule contract work to avoid the nesting season or remove nesting habitat before starting work. | PM/RE | 2012-11-24
Active | 166 | R/W | Additional R/W | Due to the complex nature of the staging, additional right of way or construction easements may be required to complete the work as contemplated, resulting in additional cost to the project. |  | 40 | 60 | 500000 | 750000 | 1000000 | 375000 | [5 empty] | Mitigate | Re-sequence the work to enable R/W Certification | R/W Person | 2012-11-24
Active | 167 | Construction | Hazardous Materials | Hazardous materials encountered during construction will require an on-site storage area and potential additional costs to dispose |  | 20 | 40 | 100000 |  | 300000 | 60000 | [5 empty] | Accept | Ensure storage space will be available | PM | 2012-11-24

## Level 2 Risk Matrix
Impact Definitions
Rating --> | Very Low | Low | Moderate | High | Very High
Cost Impact of Threat | Insignificant cost increase | <5% cost increase | 5-10% cost increase | 10-20% cost increase | >20% cost increase
(CO + COS)
Cost Impact of Opportunity (CO + COS) | Insignificant cost reduction | <1% cost decrease | 1-3% cost decrease | 3-5% cost decrease | >5% cost decrease
Schedule Impact of Threat | Insignificant slippage | <1 month slippage | 1-3 months slippage | 3-6 months slippage | >6 months slippage
Schedule Impact of Opportunity | Insignificant improvement | <1 month improvement | 1-2 months improvement | 2-3 months improvement | >3 months improvement
Probability | 1–9% | 10–19% | 20–39% | 40–59% | 60–99%
Risk Matrix
Probability Rating | 5 – Very High
4 – High
3 – Moderate
2 – Low
1 – Very Low
|  | 1 | 2 | 4 | 8 | 16
|  | Very Low | Low | Moderate | High | Very High
Impact Rating
Low Risk
Moderate Risk
High Risk