## Risk Register
| KEY: | [5 empty] | KEY:
| Client | Client Brief/ User Requirements |  |  |  |  | Key/ Critical
| Team | Consultants, Contractors, Suppliers, Procurement |  |  |  |  | Intermediate
| External | Town Planning, Third Parties, Statutory Bodies |  |  |  |  | Minor
| Design | Consultant/ Contactor Design
| Construction | Construction, Logistics, Decanting
| Handover | Project Closeout & Handover
| Operations | Operations, Maintenance, Facilities Management
RISK IDENTIFICATION & MITIGATION |  |  |  |  | RISK ASSESSMENT - RESIDUAL RISK |  |  |  |  | ACTION PLAN - RESIDUAL RISK |  |  |  | COMMENTS
Ref | Category | Risk | Potential Impact | Completed Mitigation Action (to date) | Probability | Impact | Risk Score/ Category | Cost Impact (Project Costs) [£K] | Schedule Impact [weeks] | Action Plan | Action Owner | Next Action Target Date | Date Achieved
7 | External | Uncertainty over requirement for Plant Enclosures | Additional cost if required (VE savings currently assume enclosure is not required) | The weatherproof enclosure, as requested by ICL Engineering/Maintenance teams, for the whole of the roof plant is unaffordable within the cost plan. To accommodate as much of the request as possible, the sensitive elements of the plant (electrical items) are to be enclosed in a weather tight space covering a section of the roof. Actions closed - no plant enclosure provided. | 3 | 2 | 6 |  |  | Closed | TBA | 2008-07-25 | Oct 08 | Closed
8 | External | Unwin road MEng façade for Racing Green / Formula Student Space - works may be required prior to Skempton planning consent being given | Contravention of planning law | Resolved. | 1 | 2 | 2 |  |  | Closed | PM / Planning Consultant | 2008-07-25 | end 08 | Closed
15 | Design | Existing tunnels and service ducts below ground cause problems during the works. | Stoppages on site / design changes required to co-ordinate with tunnels | Tunnels and ducts drawing issued by college but not felt to be adequate. Further discussion required with the designers. | 1 | 2 | 2 |  |  | Closed | ICL / designers / PM | 2008-07-01 | Closed
16 | Design | Part L compliance of façade to be confirmed my MLM | Additional cost and time while re-design is completed. | Statement provided by MLM has been forwarded to the tendering contractors. F+P has obtained design approval from MLM | 1 | 2 | 2 |  |  | Closed | F+P | 2008-06-20 | Closed
18 | Design | Fire Strategy and Smoke Ventilation - college fail to acceptance of proposed fire strategy (strategy may include fire fighters breaking windows.) | Delay while re-design completed. | ICL sign-off of the fire strategy has been obtained. | 1 | 2 | 2 |  |  | Closed | SR | 2008-07-01 | Closed
19 | Design | Condenser units may be required on Skempton entrance canopy | May affect planning application. | Existing condenser units are remaining. No new works required. | 1 | 2 | 2 |  |  | Closed | TBA | 2008-07-01 | Closed
20 | Design | ELS Survey - new dimensional survey does not match with record drawings. | Delay while re-design completed. | ELS survey complete. | 2 | 2 | 4 |  |  | Closed | SR | 2008-09-01 | Closed
21 | Design | Tunnels and risers requiring strip-out during the works are not properly surveyed. | Delay to construction works or risk of asbestos exposure to operatives. | TB&A to survey pipe work to establish where stripping out can occur. Details to be issued to Asbestos Surveyor to enable surveying prior to start of contract. Work completed. | 2 | 1 | 2 |  |  | Closed | TB&A |  | Closed
25 | Construction | Pre-enabling works over run impacting on the decant of Mech Eng, IDE, Student Formula and The Go Karts | Delay to the project | Monitoring of the advanced works done. | 1 | 2 | 2 |  |  | Closed | PM / Advanced Works Team | Ongoing | Closed
57 | Construction | Construction Logistics arrangements need to be fully signed-off by the college once the tender contractors have confirmed the current proposals are feasible - this includes: entrance areas, lift access, pedestrian routes, routes for users within the building, traffic measures, parking closures, deliveries and skip locations. | Disruption to College users | Confirm contractor's logistics plan with the College during the tender negotiation period | 2 | 3 | 6 |  |  | Site establishment plan to be updated to coordinate with Mech Eng and other contractors. | Arup | end April 09 | Closed
29b | External | Second Means of Escape from rooms | Design development necessary. | F+P and Sheppard Robson to develop fire routes as part of the design. | 1 | 2 | 2 |  |  | Closed | Design team | Stage D | Closed
31 | External | Coordination of Extract Grilles | Cost plan allows for 10m² of grilles. | Design developed. | 1 | 2 | 2 |  |  | Closed | F+P / TB&A | 2008-07-25 | Closed
33 | Design | Structural strength of Level 0 columns | May not support additional mezzanine floor, additional works may be required |  | 1 | 2 | 2 |  |  | Closed | ICL | 2008-07-01 | Closed
34 | Design | Activities/function of workshop space on Mezzanine floor | A 7.5kn loading has been applied to the mezzanine floor to provide flexibility, but this has not been confirmed by the occupants that it is satisfactory | Brief developed. | 1 | 2 | 2 |  |  | Closed | PM | 2008-06-05 | Closed
37 | Design | Fire Strategy | 1 hour fire rating requirement for: - separation between levels 0+1 - light wells - windows | Design updated | 2 | 3 | 6 |  |  | Closed | Design team | 2008-07-01 | Closed
40 | Design | Cleaning / Maintenance of external areas | Changes to external façade. | Design done | 1 | 2 | 2 |  |  | Closed | F+P / Design team | Stage E | Closed
41 | Design | CCTV Survey | Potential blocking up of drains | necessary surveys done | 1 | 3 | 3 |  |  | Closed | Design team |  | Closed
42 | Design | Scope creep due to the location of toilets required in the building | Rooms had to be blocked out because of the positioning of toilets as per requirements. | Liaise closely with Clive Hargreaves, ICL and the design team. | 2 | 3 | 6 |  |  | Closed | ICL/ PD/ Design team / Pm | 2008-07-24 | Closed
45 | Design | Public Health (Part H) | Possible pump requirement for Level 0 toilets | Closed. Pumps required and agreed with ICL. | 1 | 2 | 2 |  |  | Closed | Design team / MLM |  | Closed
64 | Construction | Final colour scheme and omission of ceilings may affect lighting calcs. | Additional lights may be required. | Closed. | 1 | 2 | 2 |  |  | Closed | TBA | Ongoing | Closed
R_66 | Construction | Hydrology lab, substation relocation proposed to mitigate impact of office moves on users. | Indicative costs received from Wallis for the substation relocation were significantly in excess of the expected budget. Alternative accommodation has been identified to maintain the tendered scope. | Alternative accommodation accepted in April 09. Wallis to develop scheme once PMI issued in early June 09. | 2 | 3 | 6 |  |  | Closed | Arup / Wallis |  | Closed

## Risk Scoring
Risk Scoring Matrix | [5 empty] | Probability Categories
Impact | High/ Critical | 3 | 3 | 6 | 9 | Description |  | Prob | Scale Value
| Medium/ Serious | 2 | 2 | 4 | 6 | H | Probable | >70% | 3
| Low/ Marginal | 1 | 1 | 2 | 3 | M | Could happen | 30-70% | 2
|  |  | 1 | 2 | 3 | L | Improbable | <30% | 1
|  |  | Low/ Improbable | Medium/ Could happen | High/ Probable | Impact Categories
[6 empty] | Description |  | Guide Scenario |  | Scale Value
[6 empty] | H | Critical | Failure that involves significant rework, modification or reassessment |  | 3
[6 empty] | M | Serious | Failure or setback that causes additional work and reassessment but containable |  | 2
|  |  | Probability |  |  | L | Marginal | Impact has some effect causing rework or reassessment but easily handled |  | 1
Risk Category & Action
Key/ Critical Risks - closely monitor, manage & develop fallback plans
Intermediate Risks - monitor and manage to mitigate/ include specific risk allowances in cost estimate/ programme
Minor Risks - general allowance in base cost estimate & programme