## Sheet1
Project Risk Log
[18 empty] | Qty of Risks at level | Total Approx £ impact of Risks at level |  | RiskType | Probability | Impact
|  |  | Project Ref: |  |  | HMLB 0800 | Project Name: |  | Hammersmith L Block | [7 empty] | Red | 0 | 0 |  | Business | 1.Very unlikely say 20% | 1. < £200k
|  |  | Project Manager: |  |  | EC Harris | College Customers / Business Contacts: | [9 empty] | Amber | 0 | 0 |  | Project | 2. Unlikely say 40% | 2. £ 200k-£ 500k
|  |  | Project Board: | [13 empty] | Green | 39 | 14605000 |  | Stage | 3. Likely say 60% | 3. £ 500k-£ 1.0 million
[17 empty] | Average |  | 4978800 |  |  | 4. Very likely say 80% | 4. £ 1.0 million>
ID | TYPE | AUTHOR | RISK OWNER (i.e. A.Nother) | DATE IDENTIFIED | RISK OWNER @ CONTRACT | RISK CATEGORY | DESCRIPTION | PROB | IMPACT | RISK LEVEL | Probability | APPROX IMPACT £ |  |  | Average Impact | Average Impact (£) x Prob %age | STATUS | ACTION | MITIGATION ACTION 1 | ACTION OWNER | ACTION BY DATE | MITIGATION ACTION 2 | ACTION OWNER | ACTION BY DATE | LAST UPDATED |  |  |  |  | 3rd Party Impact
[12 empty] | H | M | L
109 | Project | P Gudge |  | 2008-07-10 | Imperial College | Construction | Main contractor insolvency | 2 | 4 | 8 | 20% | 4500000 | 3000000 | 1500000 | 3000000 | 600000 | Open | Acceptance | Carry out credit checks prior to entering into contract and implement bonds etc as appropriate | ECH | 2009-01-01 | Careful monitoring of Contractor during construction period | ECH | Ongoing | 2008-07-14 | notred | notamber | green¦Open | 3000000
57 | Project | P. Chiew | EC Harris | 2008-04-30 | Imperial College | Organisation | Implementation of changes requested by tenants without agreement of funding between IC & Tenant | 2 | 3 | 6 | 50% | 500000 | 350000 | 250000 | 366666.6667 | 183333.3333 | Open | Reduction | Clearly identify areas of direct cost to tenant users | TT | Ongoing | Any proposed tenant changes to be subject to strict change control | Matt Lee | Ongoing | 2008-07-14 | notred | notamber | green¦Open | 350000
51 | Project | A. Collins | EC Harris | 2008-03-06 | Imperial College | Organisation | Extended construction programme due to amended design i.e Variations | 2 | 3 | 6 | 40% | 1000000 | 750000 | 500000 | 750000 | 300000 | Open | Prevention | Do not accept Client change during construction unless no impact upon programme | ECH | Ongoing | All changes required to go into post contract change | ECH | Ongoing | 2008-07-14 | notred | notamber | green¦Open | 750000
112 | Project | P Gudge | EC Harris | 2008-07-10 | Imperial College | Construction | Power supply not provided in accordance with programme requirements | 2 | 3 | 6 | 40% | 1000000 | 500000 | 300000 | 600000 | 240000 | Open | Acceptance | Monitor and proactively manage to ensure power supply provided on time. Transfer delivery risk to main contractor. | ECH | Ongoing | HL to request for quotation on time in order for order to be placed and cheque issued | HL | 2008-09-01 | 2008-07-14 | notred | notamber | green¦Open | 500000
132 | Project | P. Chiew | Imperial College | 2008-11-27 | Imperial College | Construction | Insufficient level of detail for commissioning | 2 | 3 | 6 | 40% | 250000 | 150000 | 100000 | 166666.6667 | 66666.6667 | Open |  | Early review and programming of commissioning and ensuring that all parties fully understand the ICL commissioning requirements | ECH | Ongoing | Robust management of the commissioning process including the early appointment of external validation engineer | ECH |  |  | notred | notamber | green¦Open | 150000
127 | Project | M.Irmiger | Imperial College | 2008-04-30 | Contractor | Design | General Design Development between Stage D & Stage E | 3 | 2 | 6 | 60% | 700000 | 450000 | 250000 | 466666.6667 | 280000 | Open |  | Design Team to review and confirm design changes during Stage E | SR | 2008-09-01 | Implementation of Change control to approve items with cost effects. | ECH | 2008-09-01 | 2009-08-15 | notred | notamber | green¦Open | 450000
79 | Project | P. Chiew | Imperial College | 2008-04-30 | Imperial College | Enabling Works & Decant Activity | Failure of management of IC decant to achieve decant by 31.03.09 | 3 | 2 | 6 | 40% | 500000 | 300000 | 200000 | 333333.3333 | 133333.3333 | Open | Reduction | Appointment of internal specialist PM and full time user coordinator to assist in decant coordination | IC | Ongoing | Coordinate and monitor decant works | ECH | Ongoing | 2008-07-14 | notred | notamber | green¦Open | 300000
133 | Project | P. Chiew | Imperial College | 2008-11-27 | Imperial College | Construction | Late selection of client direct equipment | 3 | 2 | 6 | 60% | 500000 | 300000 | 150000 | 316666.6667 | 190000 | Open |  | Ensure key milestones for selection and placing order of client direct equipment is included on the programme | ECH | Ongoing | Full engagement with users and ensure that users are aware of milestones and implication of not meeting milestones | Matt Lee |  |  | notred | notamber | green¦Open | 300000
77 | Project | P. Chiew | Hoare Lea | 2008-04-30 | Enabling Contractor | Enabling Works & Decant Activity | Damage/ disconnection of services to other campus buildings during enabling works - MAJOR ITEMS | 1 | 4 | 4 | 20% | 1400000 | 900000 | 500000 | 933333.3333 | 186666.6667 | Open | Transference | Comprehensive survey of existing services | ECH | 2008-12-01 | Desktop study of all existing services information | HL | 2008-09-01 | 2008-07-14 | notred | notamber | green¦Open | 900000
88 | Project | P Gudge | Imperial College | 2008-07-10 | Imperial College | Programme | Failure of management of ICHT decant to achieve decant by 31.03.09 | 2 | 2 | 4 | 40% | 500000 | 400000 | 300000 | 400000 | 160000 | Open | Reduction | Coordinate and monitor decant works | ECH | Ongoing |  |  |  | 2008-07-14 | notred | notamber | green¦Open | 400000
84 | Project | P. Chiew | Imperial College | 2008-04-30 | Imperial College | Enabling Works & Decant Activity | Unexpected levels of asbestos found in building structure (principally contractor risk) | 1 | 2 | 2 | 20% | 100000 | 75000 | 50000 | 75000 | 15000 | Open | Reduction | Ensure contractor carries out Type 3 asbestos survey | ECH | 2008-12-01 | Ensure demolition contract accounts for disposal of contaminated waste | TT | 2008-09-01 | 2008-07-14 | notred | notamber | green¦Open | 75000
60 | Project | P. Chiew | Imperial College | 2008-04-30 | Imperial College | Organisation | User dissatisfaction with output compared to expectations | 2 | 2 | 4 | 40% | 500000 | 350000 | 150000 | 333333.3333 | 133333.3333 | Open | Reduction | Manage user expectations during design & construction | IC (user coordinator) | Ongoing | Appoint full time user coordinator | IC |  | 2008-07-14 | notred | notamber | green¦Open | 350000
81 | Project | P. Chiew | Imperial College | 2008-04-30 | Shared Imperial and Contractor | Enabling Works & Decant Activity | Disruption caused by demolition works is unacceptable to neighbouring buildings | 2 | 2 | 4 | 40% | 350000 | 200000 | 75000 | 208333.3333 | 83333.3333 | Open | Reduction | Acoustic enhances 4m high boarding to be priced | TT | Ongoing | Contractor appointed for a 6 day week | ECH | 2008-12-01 | 2008-07-14 | notred | notamber | green¦Open | 200000
73 | Project | P. Chiew | Imperial College | 2008-04-30 | Imperial College | Design | Lack of interface between client and design team leading to unsuitable provision of equipment and inadequate furniture | 2 | 2 | 4 | 40% | 300000 | 200000 | 100000 | 200000 | 80000 | Open | Reduction | Ensure that client suppliers are fully on board with the scheme and are informed about the scheme | ECH | Ongoing | Meetings to be convened between user coordinator and SR/HL to ensure suitability of provisions | ECH | Ongoing | 2008-07-14 | notred | notamber | green¦Open | 200000
121 | Project | P. Chiew | EC Harris | 2008-09-08 | Imperial College | Programme | Late finish of CWB Phase 3 project [Risk: order of magnitude assumed in order of 2 weeks] | 2 | 2 | 4 | 40% | 300000 | 250000 | 150000 | 233333.3333 | 93333.3333 | Open |  | Regular liason with the CWB project team to ensure they are aware of impact of completion of CBW for L/J blocks | ECH | Ongoing | Ensure early warnings on delays are communicated in order for joint mitigation actions to be produced | ECH | Ongoing |  | notred | notamber | green¦Open
130 | Project | P. Chiew | Imperial College | 2008-11-27 | Contractor | Construction | Sub contractor insolvency | 3 | 2 | 6 | 60% | 200000 | 150000 | 50000 | 133333.3333 | 80000 | Open |  | Main contractor carry out credit checks prior to entering into contract and implement bonds etc as appropriate | Main Contractor | Ongoing | Main Contractor careful monitoring of sub contractor during construction period | Main Contractor | Ongoing |  | notred | notamber | green¦Open
131 | Project | P. Chiew | Imperial College | 2008-11-27 | Imperial College | Tender | Deficencies to Employers Requirement | 2 | 2 | 4 | 40% | 1000000 | 500000 | 250000 | 583333.3333 | 233333.3333 | Open |  | Comprehensive review of tender deliverables prior to going out to tender | T&T | 2009-01-31 |  |  |  |  | notred | notamber | green¦Open
104 | Project | P Gudge | Imperial College | 2008-07-10 | Imperial College | Programme | Changes of potential occupants leads to changes to design solution [Minor only - assumed significant change of use funded through separate budget/funding] | 4 | 1 | 4 | 80% | 200000 | 150000 | 100000 | 150000 | 120000 | Open | Reduction | Implement strict change control during construction and implement major changes post contract. | ECH | Ongoing |  |  |  | 2008-07-14 | notred | notamber | green¦Open | 150000
106 | Project | P Gudge | Hoare Lea | 2008-07-10 | Main Contractor | Design | Poor performance of sub cocntractor for engineering elements [Additional Management costs to ICL - contractor risk] | 4 | 1 | 4 | 80% | 100000 | 75000 | 50000 | 75000 | 60000 | Open | Reduction | Comprehensive evaluation of sub contractor designers as part of main tender evaluation. | ECH | 2009-04-01 |  |  |  | 2008-07-14 | notred | notamber | green¦Open | 75000
122 | Project | P. Chiew | Sheppard Robson | 2008-09-08 | Contractor | Design | Future ammendments to ICL standards and procedures leads to the requirement for changing the design | 4 | 1 | 4 | 75% | 200000 | 150000 | 50000 | 133333.3333 | 100000 | Open |  | Review any ammendments to ICL standards and procedures when issued | ECH | Ongoing | Advice implementation of ammended ICL standards prior to inclusion within project | ECH | Ongoing |  | notred | notamber | green¦Open
66 | Project | P. Chiew | Hoare Lea | 2008-04-30 | Main Contractor | Design | Chill beam detailed design solution is not suitable for purpose | 1 | 3 | 3 | 20% | 1000000 | 750000 | 250000 | 666666.6667 | 133333.3333 | Open | Transference | Chilled beams mock up to be carried out | HL | 2009-05-01 | Ensure that users have an understanding of the chilled beam system to be provided | HL | 2008-09-01 | 2008-07-14 | notred | notamber | green¦Open | 750000
69 | Project | P. Chiew | Imperial College | 2008-04-30 | N/A | Design | Reserve Matters not met - additional cost required to meet detailed planning conditions | 1 | 1 | 1 | 10% | 250000 | 150000 | 100000 | 166666.6667 | 16666.6667 | Open | Acceptance | Regular discussions with LBHF to ensure they are satisfied with the progress of the design | SR | 2008-12-01 | Discharge conditions as soon as possible | SR | 2009-05-01 | 2008-07-14 | notred | notamber | green¦Open | 150000
129 | Project | P. Chiew | Imperial College | 2008-11-03 | Imperial College | Enabling Works & Decant Activity | No alternative location has been identified for the multi faith Prayer Room | 1 | 3 | 3 | 20% | 10000 | 5000 | 2000 | 5666.6667 | 1133.3333 | Open |  | Coordinate and monitor decant works | ECH | 2009-03-01 |  |  |  |  | notred | notamber | green¦Open | 5000
77A | Project | P. Chiew | Hoare Lea | 2008-04-30 | Enabling Contractor | Enabling Works & Decant Activity | Damage/ disconnection of services to other campus buildings during enabling works - MINOR ITEMS | 3 | 1 | 3 | 80% | 150000 | 100000 | 50000 | 100000 | 80000 | Open | Transference | Comprehensive survey of existing services | ECH | 2008-12-01 | Desktop study of all existing services information | HL | 2008-09-01 | 2008-07-14 | notred | notamber | green¦Open | 100000
56 | Stage | P. Chiew | Imperial College | 2008-04-30 | Imperial College | Organisation | Delay to sign off of change orders within the scheme leading to uncertainty regarding cost and time | 1 | 2 | 2 | 20% | 750000 | 500000 | 250000 | 500000 | 100000 | Open | Reduction | Ensure sign off all change orders prior to Stage E report sign off | ECH | 2009-01-01 | Ensure change orders signed off as created | ECH | Ongoing | 2008-07-14 | notred | notamber | green¦Open | 500000
52 | Project | A. Collins | EC Harris | 2008-03-06 | Contractor | Organisation | Indequate commissioning and validation of facility leading to dissatisfied users post occupation | 1 | 2 | 2 | 20% | 350000 | 250000 | 200000 | 266666.6667 | 53333.3333 | Open | Reduction | Ensure revised ICL commissionning & validation standards and procedures are included within tender docuemnt | TT / Design Team | 2009-01-01 | Milestone for 'booking of ICL validators' to be included within the programme | ECH | 2008-09-01 | 2008-07-14 | notred | notamber | green¦Open | 250000
50 | Project | A. Collins | T & T | 2008-03-06 | Imperial College | Organisation | Cost Plan exceeds budget because of inability to undertake extensive market testing of cost plan due to insufficient/late design information | 1 | 2 | 2 | 10% | 500000 | 350000 | 250000 | 366666.6667 | 36666.6667 | Open | Reduction | Early release of key design packages to the cost consultant | SR | Ongoing | TT to ensure DT are fully aware of what and when key packages are required. | TT | Ongoing | 2008-07-14 | notred | notamber | green¦Open | 350000
55 | Stage | P. Chiew | EC Harris | 2008-04-30 | N/A | Organisation | Impact of duty holder comments of Stage E/tender package on tender programme | 1 | 2 | 2 | 20% | 400000 | 250000 | 100000 | 250000 | 50000 | Open | Reduction | Clearly defined sign off process | ECH | 2009-01-01 |  |  |  | 2008-07-14 | notred | notamber | green¦Open | 250000
P. Chiew | Project | P. Chiew | Hoare Lea | 2008-04-30 | Imperial College | Enabling Works & Main Works | Unforeseen obstruction (in the ground) | 1 | 2 | 2 | 20% | 200000 | 150000 | 100000 | 150000 | 30000 | Open | Reduction | Review all service information | ECH | 2008-12-01 | Scan prior to any excavation works | ECH | 2008-10-01 | 2008-07-14 | notred | notamber | green¦Open | 150000
P. Chiew | Project | P. Chiew | Imperial College | 2008-04-30 | Imperial College | Organisation | Timescales for the installation of HH CHP does not coincide with Block L project | 1 | 2 | 2 | 15% | 750000 | 500000 | 250000 | 500000 | 75000 | Open | Reduction | Regular programme discussions between Block L team and ICHT to ensure both projects tie in | ECH | Ongoing | Ensure legal documentation in place between IC/ ICHT to guarantee delivery | IC (AS) | 2008-09-01 | 2008-07-14 | notred | notamber | green¦Open | 500000
P. Chiew | Project | P. Chiew | Imperial College | 2008-07-10 | Imperial College | Programme | Liquidated damages are insufficient to cover ICL's cost if construction is in delay | 1 | 2 | 2 | 20% | 250000 | 200000 | 100000 | 183333.3333 | 36666.6667 | Open | Acceptance | ICL to advice proper calculation of damages | ICL | 2008-12-01 |  |  |  | 2008-07-14 | notred | notamber | green¦Open | 200000
P Gudge | Project | P Gudge | Hoare Lea | 2008-07-10 | Hoare Lea | Design | Detailed aspects of Engineering services of design not in accordance with IC published standards | 1 | 2 | 2 | 20% | 500000 | 350000 | 100000 | 316666.6667 | 63333.3333 | Open | Reduction | Ensure specification complies with IC requirements | HL | 2008-12-01 | Duty Holder review | ECH | 2008-12-01 | 2008-07-14 | notred | notamber | green¦Open | 350000
P Gudge | Project | P Gudge | Sheppard Robson | 2008-07-10 | Sheppard Robson | Design | Architectural aspects of design not in accordance with IC published standards | 1 | 2 | 2 | 20% | 250000 | 200000 | 150000 | 200000 | 40000 | Open | Reduction | Ensure specification complies with IC requirements | SR | 2008-12-01 | Duty Holder review | ECH | 2008-12-01 | 2008-07-14 | notred | notamber | green¦Open | 200000
P Gudge | Project | P Gudge | Imperial College | 2008-07-10 | Contractor | Programme | Inadequate commissioning time allocated within construction/delivery programme | 1 | 2 | 2 | 20% | 500000 | 400000 | 100000 | 333333.3333 | 66666.6667 | Open | Reduction | Clarify within tender documentation commissioning requirements and critically evaluate contractor's programme | ECH | 2009-04-01 | Ensure adequate commissioning time within tender docs and specify items required for commissioning | TT | 2008-12-01 | 2008-07-14 | notred | notamber | green¦Open | 400000
P Gudge | Project | P Gudge | Imperial College | 2008-07-10 | Imperial College | Enabling Works & Decant Activity | Space allocated for decant staff insufficient. | 1 | 2 | 2 | 10% | 250000 | 200000 | 150000 | 200000 | 20000 | Open | Reduction | Monitor IC decant programme and ensure corrective action if required | IC (user coordinator) | Ongoing | Confirmation of scope of works for areas where IC personnelwill decant to | IC (user coordinator) | 2008-09-01 | 2008-07-14 | notred | notamber | green¦Open | 200000
P. Chiew | Project | P. Chiew | Sheppard Robson | 2008-04-30 | Contractor | Design | Areas of design where crossover occurs between IC and ICHT do not meet ICHT standards | 1 | 2 | 2 | 20% | 500000 | 250000 | 100000 | 283333.3333 | 56666.6667 | Open | Reduction | Single point of contact within ICHT to disseminate information | ECH | 2008-07-01 | ICHT stakeholders to review drawings which affect the ICHT areas | Design Team | 2008-12-01 | 2008-07-14 | notred | notamber | green¦Open | 250000
P. Chiew | Project | P. Chiew | Sheppard Robson | 2008-09-08 | Contractor | Design | Several aspects of the design would need to be amended to accommodate requirements of alternative specialist equipment - current design is based on Siemens | 1 | 2 | 2 | 20% | 500000 | 300000 | 200000 | 333333.3333 | 66666.6667 | Open |  | ICHT/ICL to re-confirm that Siemens is the preferred equipment Supplier | SR | 2008-09-01 | ICHT/ICL to advice within a timely manner if they wish to proceced with an alternative equipment specialist to ensure minimal impact on the programme | ICL | Ongoing |  | notred | notamber | green¦Open
P. Chiew | Project | P. Chiew | Imperial College | 2008-11-03 | Imperial College | Enabling Works & Decant Activity | Delay in achieving the J Block outline planning consent impacting on the commencement of the demolition of J block | 1 | 2 | 2 | 20% | 250000 | 150000 | 75000 | 158333.3333 | 31666.6667 | Open |  | Currently there is a 8 week mobilisation period after the appointment of the demolition contractor prior to the commencement of demolition |  |  | Demolition Contractor to start demolishing L block first
P. Chiew | Project | P. Chiew | Imperial College | 2008-11-27 | Imperial College | Construction | Lack of coordination between contractor and client direct equipment | 1 | 2 | 2 | 20% | 250000 | 150000 | 100000 | 166666.6667 | 33333.3333 | Open |  | Ensure full coordination between users and contractor including early visibility of Group 2/3 equipment | ECH | Ongoing | Full engagement with users and ensure that users are aware of milestones and implication of not meeting milestones | Matt Lee
P. Chiew | Project | P. Chiew | Imperial College | 2008-04-30 | Imperial College | Design | Boreholes do not yield sufficient amount to satisfy the GLA | 2 | 1 | 2 | 20% | 500000 | 350000 | 150000 | 333333.3333 | 66666.6667 | Open | Reduction | Carry out desktop study & site investigation to verify borehole suitability | HL | 2008-07-01 | Ensure sustainable alternatives are available | HL | 2008-07-01 | 2008-07-14 | notred | notamber | green¦Open | 350000
P Gudge | Project | P Gudge | Sheppard Robson | 2008-07-10 | Imperial College | Design | Poor performance of architectural elements suppliers i.e. supplier of keys/locks |  |  | 0 | 40% | 50000 | 40000 | 30000 | 40000 | 16000 | Open | Reduction | Comprehensive evaluation of suppliers as part of main tender evaluation. | ECH | 2009-04-01 |  |  |  | 2008-07-14 | notred | notamber | notgreen | 40000
M.Irmiger | Project | M.Irmiger | Imperial College | 2009-01-20 | Imperial College | Construction | Market Volitility:- Reduced prices / inflation allowance within cost plan. Potential risk priced by Tenderers exceeds adjusted Cost Plan Allowances | 2 | 4 | 8 | 40% | 2000000 | 1500000 | 750000 | 1416666.6667 | 566666.6667 | Open | Transference | Inflation / Deflation agreements to be clearly identified with main contractor during contract negotiations | TT | 2009-06-01 | Risk to be transferred to main contractor | TT | 2009-06-01 | 2009-01-20 | notred | notamber | green¦Open | 1500000
- 109 | [7 empty] | 2009-01-26
P Gudge |  | P Gudge | EC Harris | 2008-07-10 | Imperial College | Organisation | Lack of familiarity with contract form amongst the design team leading to administration errors |  |  | 0 | 0% | 300000 | 200000 | 50000 | 183333.3333 | 0 | Closed | Reduction | Ensure all design team clear regarding responsibilities and implement training if required | ECH | 2008-10-01 |  |  |  | 2008-07-14 | notred | notamber | notgreen | 200000
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Specific requirements in terms of development floor areas |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Specific requirements in terms of car park areas |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Further information for the environmental impact assessment |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Presence of additional asbestos e/o survey findings |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Unforseen information required for the Green Transport Plan |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Additional highway works requirement |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Rights of way/light issues |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Legal negotiations with the Trust |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Assumed design brief for Stage D report |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Undefined specialist facilities that are to be incorporated into the design |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Differences between generic labs vs specialised labs |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Changes in security & FM strategy |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Unforseen site wide issues |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Timeous sign off by key stakeholders and duty holders of Stage D report |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | User requirements for Block L/J phasing |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Unforseen problems with ongoing maintenance and operation of A&E facilities |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Maintaining Block J corridor structurally |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Impact of service tunnel on new structure/foundation |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Problems with existing drainage |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Land ownership/boundary disputes i.e. LMC ownership |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Restrictions imposed by Special Trustees |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Separation/isolation of Block J services |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Further maintenance of safe access - J Block corridor |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Maintenance of full use of Block J throughout development programme |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Developing Block L design without considering Block J - future planning permission for Block J will not be granted |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Over/Under sizing of Block L |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Cost of project rises above funding available |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Electrical utilities provision - unavailability of sufficient power to servce the project M&E requirements |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Performance of mixed mode ventilation systems - the current proposals for ventilation to the project buildings may not be preferred by the client. Air conditioning scheme may be required which is significantly more expensive |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Delay to programme |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Site constraints due to proximity of A&E |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Changes in legislation |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Unforseen ground conditions |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Availability of competent contractors |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Industrial action during construction |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Tenders returned over budget |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Client changes during construction |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Block J separation scope creep |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Block J separation detailed design process |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2007-03-04 |  |  | Possible need for sprinklers |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins |  | A. Collins | Imperial College | 2008-03-06 |  |  | Radioactive decontamination e/o survey findings |  |  | 0 | [6 empty] | Closed | [7 empty] | 2008-07-14 | notred | notamber | notgreen | 0
P Gudge | Project | P Gudge | Imperial College | 2008-07-10 | Imperial College | Construction | Lead-in for HH CHP impacts adversly upon Block L construction |  |  | 0 | 0% | [5 empty] | Closed | Acceptance | DUPLICATOIN - SEE ITEM 59 | [5 empty] | 2008-07-14 | notred | notamber | notgreen | 0
R.Hanson | Project | R.Hanson | Imperial College | 2008-05-23 |  | Construction | Access to site and associated buildings to undertake works not granted in line with programme |  |  | 0 | [6 empty] | Closed | Prevention | Ensure that required access dates are clearly identified and ensure approvals in place in advance | ECH |  |  |  |  | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins | Project | A. Collins | Imperial College | 2007-03-04 |  | Organisation | Facilities provided for decanted staff are of an insufficient standard |  |  | 0 | [6 empty] | Closed | Acceptance | Confirm fit-out requirements and IC decant protocol | IC | 2009-01-01 | Regular dialogue with stakeholders and reassessment where required | IC | 2009-01-01 | 2008-07-14 | notred | notamber | notgreen | 0
P. Chiew | Project | P. Chiew | Imperial College | 2008-04-30 |  | Organisation | Delay in completion of accommodation for decanted departments |  |  | 0 | [6 empty] | Closed | Acceptance | Ensure scope for decant areas are fully defined and frozen | IC | ? | Aggressive management of programme to ensure key dates are achieved | ECH | Ongoing | 2008-07-14 | notred | notamber | notgreen | 0
P. Chiew | Project | P. Chiew | Imperial College | 2008-04-30 |  | Design | Numerous/ late design changes leading to poor coordination within the design team |  |  | 0 | [6 empty] | Closed | Acceptance | Compile comprehensive change log | ECH | 2008-12-01 | Regular design team meetings to discuss design changes and enhancement | SR | 2008-12-01 | 2008-07-14 | notred | notamber | notgreen | 0
P. Chiew | Project | P. Chiew | Imperial College | 2008-04-30 |  | Enabling Works & Decant Activity | Works interfering with main services supply to adjacent premises |  |  | 0 | [6 empty] | Closed | Acceptance | Ensure all services are accounted for before commencement on site | Hoare Lea | 2008-12-01 | Ensure adjoining premises have back up services | IC/ ICHT | 2008-12-01 | 2008-07-14 | notred | notamber | notgreen | 0
A. Collins | Project | A. Collins | Imperial College | 2007-03-04 |  | Organisation | Unforseen end user requirements |  |  | 0 | [6 empty] | Closed | Acceptance | Vigorous change control process | ECH | Ongoing | Ensure financial provision within cost plan | TT | Ongoing | 2008-07-14 | notred | notamber | notgreen | 0
P. Chiew | Project | P. Chiew | Imperial College | 2008-04-30 |  | Organisation | Insufficient information issued to site users on imminent disruption caused by the project |  |  | 0 | [6 empty] | Closed | Acceptance | Forum to be set up to inform all HH occupants of impending works and disruption | IC | 2008-12-01 | Combined project handbook to be issued | ECH | 2008-12-01 | 2008-07-14 | notred | notamber | notgreen | 0
P. Chiew | Project | P. Chiew | Imperial College | 2008-04-30 | N/A | Organisation | Agreement not reached on HH CHP prior to commencement of Stage E |  |  | 0 | [6 empty] | Closed | Reduction | Ensure ICHT are aware of drop dead date for Block L project | Hoare Lea | 2008-05-19 |  | Hoare Lea | 30/5//2008 | 2008-07-14 | notred | notamber | notgreen | 0
P. Chiew | Project | P. Chiew | Imperial College | 2008-04-30 |  | Design | Security provided in building inadequate due to IC not provided design team with formal brief |  |  | 0 | [6 empty] | Closed | Acceptance | IC to provide formal security brief | IC | 2008-06-30 |  |  |  | 2008-07-14 | notred | notamber | notgreen | 0
P. Chiew | Project | P. Chiew | Imperial College | 2008-04-30 |  | Design | Aspects of design not in accordance to project brief |  |  | 0 | [6 empty] | Closed | Acceptance | Coordination and design review | IC | 2008-06-30 |  |  |  | 2008-07-14 | notred | notamber | notgreen | 0
P Gudge | Project | P Gudge | Imperial College | 2008-07-10 |  | Construction | Commissioning problems encountered post handover with engineering services performance (repeat ID 52) |  |  | 0 | [6 empty] | Closed | Reduction | Ensure commissioning pre-handover correctly executed and do not allow partial possession | IC (AS) | PC |  |  |  | 2008-07-14 | notred | notamber | notgreen | 0
P Gudge | Project | P Gudge | Imperial College | 2008-07-10 |  | Construction | Discharge of planning conditions more onerous than anticipated ( repeat ID 69) |  |  | 0 | [6 empty] | Closed | Acceptance | Allow appropriate construction contingency | TT | 2008-12-01 |  |  |  | 2008-07-14 | notred | notamber | notgreen | 0
P. Chiew |  | P. Chiew | EC Harris | 2008-09-28 |  | Design | User requirements received post Stage D has highighted further substantial requirements |  |  | 0 | [6 empty] | Closed |  | Project Team to meet to agree and propose conpensatory savings to the College | ECH | [5 empty] | notred | notamber | notgreen
P. Chiew |  | P. Chiew | Imperial College | 2008-09-28 |  | Programme | Delay to ICHT A&E fit out/ refurbishment project impacting on decant out of J Block |  |  | 0 | [6 empty] | Closed |  | ICHT to review the programme to ensure that contingency can be incorporated | ECH | [5 empty] | notred | notamber | notgreen
P. Chiew |  | P. Chiew | EC Harris | 2008-09-28 |  | Programme | Impact of user comments on Stage E design programme |  |  | 0 | [6 empty] | Closed |  | Instruction required so that the design team are able to incorporate changes. | ECH | [5 empty] | notred | notamber | notgreen
P. Chiew | Project | P. Chiew | Imperial College | 2008-04-30 | Contractor | Design | Site investigation reveals evidence of contamination in ground |  |  |  | 0% | 750000 | 500000 | 250000 | 500000 | 0 | Closed | Acceptance | Ensure cost allowance in project budget | TT | 2008-09-01 | Carry out desk study on history of site to identify potential issues | SR | 2008-09-01 | 2008-07-14 | notred | notamber | notgreen | 500000
A. Collins | Business | A. Collins | Imperial College | 2007-03-04 | N/A | Organisation | Development of hospital masterplan strategies impacting on Block L project |  |  |  | 0% | 2000000 | 1000000 | 150000 | 1050000 | 0 | Closed | Acceptance | Liason with ICL/ ICHT/ Project Board | ECH | Ongoing |  |  |  | 2008-07-14 | notred | notamber | notgreen | 1000000
Imperial College | Stage | P. Gudge | Imperial College | 2008-07-10 | Imperial College | Enabling Works & Decant Activity | Failure to clear all radiation from existing accommodation |  |  |  | 0% | 500000 | 350000 | 200000 | 350000 | 0 | Closed | Reduction | Ensure all activities necessary to identify and remove radiation are included in decant process | ECH | 2009-03-01 |  |  |  | 2008-07-14 | notred | notamber | notgreen | 350000
Imperial College | Business | P Gudge | Imperial College | 2008-07-10 | Imperial College | Construction | General engineering services quality does not meet Client expectations |  |  |  | 0% | 250000 | 200000 | 150000 | 200000 | 0 | Closed | Reduction | Ensure sign off process sets out qualitative expectations | ECH | 2008-12-01 |  |  |  | 2008-07-14 | notred | notamber | notgreen | 200000
103 | Business | P Gudge | Imperial College | 2008-07-10 | Imperial College | Construction | General building quality does not meet Client expectations |  |  |  | 0% | 250000 | 200000 | 150000 | 200000 | 0 | Closed | Reduction | Ensure sign off process sets out qualitative expectations | ECH | 2008-12-01 |  |  |  | 2008-07-14 | notred | notamber | notgreen | 200000
106 | Project | P Gudge | Curtins Consulting | 2008-07-10 | Imperial College | Design | Poor performance of key supply chain designers for structural engineering elements |  |  |  | 0% | 250000 | 200000 | 150000 | 200000 | 0 | Closed | Reduction | Comprehensive evaluation of key supply chain designers as part of main tender evaluation. | ECH | 2009-02-01 |  |  |  | 2008-07-14 | notred | notamber | notgreen | 200000
113 | Project | P Gudge | Imperial College | 2008-07-10 | Imperial College | Programme | Failure to meet user drainage requirements |  |  |  | 0% | 250000 | 200000 | 150000 | 200000 | 0 | Closed | Reduction | Sign off process to clarify requirements | ECH | 2008-10-01 |  |  |  | 2008-07-14 | notred | notamber | notgreen | 200000
63 | Project | P. Chiew | Imperial College | 2008-04-30 | Contractor | Design | Site specific geotechnical information differs from information from neighbouring site, which has been used to inform the design to date |  |  |  | 0% | 500000 | 250000 | 150000 | 300000 | 0 | Closed | Contingency | Ensure that site specific geotechnical information is used in the design moving forward | CC |  |  |  |  | 2008-07-14 | notred | notamber | notgreen | 250000
98 | Stage | P Gudge | Imperial College | 2008-07-10 | Imperial College | Design | Retention of Block 136 impacts adversley upon demolition and rebuild programme |  |  |  | 0% | 500000 | 250000 | 100000 | 283333.3333 | 0 | Closed | Reduction | Ensure detailed planning exercise to minimise impact of retention or if not viable recommend demolition of Block 136 | ECH | 2008-08-01 |  |  |  | 2008-07-14 | notred | notamber | notgreen | 250000
116 | Stage | P Gudge | Imperial College | 2008-07-10 | Imperial College | Design | Retention of first floor meeting room to Block B impacts adversley upon demolition and rebuild programme |  |  |  | 0% | 300000 | 200000 | 150000 | 216666.6667 | 0 | Closed | Reduction | Ensure detailed planning exercise to minimise impact of retention or if not viable recommend demolition of first floor meeting room | ECH | 2008-08-01 |  |  |  | 2008-07-14 | notred | notamber | notgreen | 200000
34 | Project | A. Collins | Design Team | 2007-03-04 | Design Team | Design | Additional requirement to achieve BREEAM excellent rating as required by Imperial ( revised requirement since Stage D) |  |  |  | 0% | 100000 | 50000 | 0 | 50000 | 0 | Closed | Prevention | Design Team to agree required measures; Current BREEAM assessment to be confirmed - additional requirements to be identified and request for funding to be submitted to client / funded from VE | Hoare Lea | 2008-08-01 | Ensure financial provision within cost plan | TT |  | 2008-07-14 | notred | notamber | notgreen | 50000
54 | Stage | P. Gudge | EC Harris | 2008-07-10 | Imperial College | Organisation | Delay to Stage E sign off by user groups |  |  |  | 0% | 150000 | 100000 | 50000 | 100000 | 0 | Closed | Reduction | Clearly defined sign off procedure | ECH | 2008-10-01 |  |  |  | 2008-07-14 | notred | notamber | notgreen | 100000
49 | Project | A. Collins | Turner & Townsend | 2008-03-06 | Main Contractor | Organisation | "Abnormally high" inflation of raw material prices leading to higher metal & materials costs than anticipated |  |  |  |  | 1000000 | 650000 | 350000 | 666666.6667 | 0 | Closed | Acceptance | Monitor pre-contract market conditions | TT | Ongoing | Pass future risk on inflation to Contractor | TT | 2009-05-01 | 2008-07-14 | notred | notamber | notgreen | 650000
114 | Project | P Gudge | EC Harris | 2008-07-10 | Imperial College | Construction | Scope gaps between enabling and main construction works; specific contingency within Stage D for finalised scope |  |  |  |  | 400000 | 350000 | 250000 | 333333.3333 | 0 | Closed | Reduction | Detailed evaluation of enabling and main construction works by design team to ensure no gaps | ECH | 2008-09-01 | Ensure coordination between design team | SR | 2008-09-01 | 2008-07-14 | notred | notamber | notgreen | 350000
48 | Project | A. Collins | Turner & Townsend | 2008-03-06 | Imperial College | Organisation | Indequate market engagement & response through competitive tendering |  |  |  |  | 3500000 | 2500000 | 1500000 | 2500000 | 0 | Closed | Reduction | PQQ/ Engage Contractors | ECH | 2008-11-01 | Ensure sufficient PQQ contractors and monitor/liaise with tenderers to ensure 'no surprises' | TT | 2008-11-01 | 2008-07-14 | notred | notamber | notgreen | 2500000
1 | Project | A. Collins | Imperial College | 2007-03-04 | Imperial College | Statutory/ Legislative | Unforseen additional renewables/LZC technology requirements from GLA (GLA changing benchmark) |  |  |  |  | 750000 | 500000 | 250000 | 500000 | 0 | Closed | Acceptance | None | [5 empty] | 2008-07-14 | notred | notamber | notgreen | 500000
65 | Project | P. Chiew | Imperial College | 2008-04-30 | Imperial College | Design | UXB discovered on site |  |  |  |  | 1000000 | 500000 | 50000 | 516666.6667 | 0 | Closed | Reduction | Desktop study for UXB to be undertaken | ECH | 2008-09-01 |  |  |  | 2008-07-14 | notred | notamber | notgreen | 500000
95 | Project | P Gudge | Imperial College | 2008-07-10 | Imperial College | Enabling Works & Decant Activity | Space allocated by ICHT for decant staff insufficient.[max 4 week delayed commencement] |  |  |  |  | 400000 | 250000 | 150000 | 266666.6667 | 0 | Closed | Reduction | Monitor ICHT decant programme and ensure corrective action if required | ECH | Ongoing |  |  |  | 2008-07-14 | notred | notamber | notgreen | 250000
96 | Project | P Gudge | Hoare Lea | 2008-07-10 | Hoare Lea | Design | Insufficient provision of engineering spares/consumables incorporated in contract |  |  |  |  | 75000 | 50000 | 25000 | 50000 | 0 | Closed | Reduction | HL/ICL to specify spares required | HL | 2008-10-01 | Ensure provisions incorporated in tender | TT | 2008-12-01 | 2008-07-14 | notred | notamber | notgreen | 50000
99 |  | P Gudge | Imperial College | 2008-07-10 | Imperial College | Programme | Funding for re-cant following construction inadequate |  |  |  |  | 150000 | 100000 | 50000 | 100000 | 0 | Closed | Acceptance | Provisional Allowance included within Stage D Cost Plan | ECH | 2008-09-01 | IC to implement activity to ensure adequate funds allocated | ICL |  | 2008-07-14 | notred | notamber | notgreen | 100000
117 |  | P. Chiew | Imperial College | 2008-08-13 | Imperial College | Organisation | Increased cost of ICHT Trust decant project (except for unschedule care/ infection control) will be passed on to ICL (50% of total cost - previously £7.722m, currently £12.6m) |  |  | 0 | [6 empty] | Closed |  | ICL to reconfirm to ICHT that the ICL contribution is a lump sum figure as previously agreed: RISK OUTSIDE PROJECT CONTINGENCY FUNDING | ICL | [5 empty] | notred | notamber | notgreen
99 |  | P Gudge | Imperial College | 2008-07-10 | Imperial College | Programme | Funding for re-cant following construction inadequate |  |  |  |  | 150000 | 100000 | 50000 | 100000 | 0 | Closed | Acceptance | Provisional Allowance included within Stage D Cost Plan | ECH | 2008-09-01 | IC to implement activity to ensure adequate funds allocated | ICL |  | 2008-07-14 | notred | notamber | notgreen | 100000
70 | Project | P. Chiew | Sheppard Robson | 2008-04-30 | N/A | Design | Planners require extensive alteration to south façade due to the demolition of Block J |  |  |  |  | 500000 | 350000 | 200000 | 350000 | 0 | Closed | Acceptance | Ensure cost allowance in project budget to upgrade south façade | TT | 2008-12-01 | Ensure planners are kept informed of progress | SR | 2008-08-01 | 2008-07-14 | notred | notamber | notgreen | 350000
INSERT NEW RISK ABOVE
Formulas:
PROB = IF([2]Contents!$N18="Please Enter","Enter Date on Contents Page",[2]Contents!$N18)
Note on H130: IrmigMik: Requires any additional works to be funded from VE / other - i.e. not funded thro' contingency
Note on H131: IrmigMik: included with item 55
Note on J38: IrmigMik: Impact of contamination included under 64