## Instructions
Sport England Generic Risk Register
Guidance
This Risk Register has been designed to assist Lottery Applicants, Design Teams and Facility Operators in the consideration and management of risk on their projects. The register has been complied to meet Best Practice in accordance with recognised Project Management methodologies such as PRINCE2, the risk categories reflect PRINCE2 principles.
The register is generic and is intended to promote the consideration of risk. Users are not expected to use every risk, but to consider those that may be applicable to their Project, or where a similar, related risk may be applicable to their project.
The identified risks can be used to compile a Strategic Risk Register or a Construction Project Risk Register.
The use of this particular Risk Register is not mandatory on Sport England Lottery Funded projects; Applicants may use their own format. Applicants must however be aware that the consideration of Risk by Applicants and how Risk is managed on Projects is often a condition of a grant award.
The inherent and residual risk columns contain formulae that calculate the risk exposure; the residual risk exposure should always be no worse that the inherent risk exposure.
The financial impact column has been deliberately left blank without any formulae as the financial impact can be calculated in various ways. Applicants should consult with their Professional Advisors in this respect.
If the register is used to compile a Construction Project Risk Register, the total of the Financial Impact should equate to the Project Contingency at any stage of the Project.
Closed Risks can be moved from the Current Risk worksheet to the Closed Risks worksheet.
Risk Definitions
Impact
High = severe impact on a project in terms of time, cost or quality Severe impact on the project strategy, adverse effect on project outcome or operational activities Major stakeholder concern
Medium = significant impact on the project in terms of time, cost or quality Significant impact on the project strategy, outcome or operational activities Significant stakeholder concern
Low = minor impact on a project in terms of time, cost or quality Little impact on the project strategy, outcome or operational activities Low stakeholder concern
Likelihood
High = certain or strong possibility that it will occur, 61-100% probability
Medium = moderate chance of occurring , 41-60% probability
Low = unlikely or very unlikely to occur, 0-41% probability
Exposure
High = will have severe adverse effect on a Project
Medium = attention needed to avoid risk escalation
Low = likely to disappear
Risk Register Template - Instructions for Using Risk Spreadsheets
To start entering risk data simply follow the on-screen guidance on the attached sheet by using the mouse button to hover over the red check mark in each corner of the headings.
If you enter more rows you will need to cut and paste into the new cells the formula used to calculate exposure automatically (columns G-H and K-L).
To filter the columns (e.g. to show only the high exposure risks)
1 - press Ctrl + a to turn on filter
2 - select what you want to see from the drop-down menu that appears at the top of the relevant column
3 - press Ctrl +o to turn off the filter and show all rows again

## Current risks
No | Date last reviewed | Risk description | Category | Owner (Accountable) | Manager (Responsible) | Inherent Risk |  |  | Measures in place to Manage the Risk | Residual risk |  |  | Financial Impact £k | Further action | Status | Comments on Status | Target Closure Date
a | c | d |  | e | f | Impact | Likelihood | Exposure | j | Impact | Likelihood | Exposure | (Estimated) | p | o
Sport England Generic Risk Register - Current Risks Schedule
Version 1.0 05_Mar 12 |  |  | Category
Risk Categories:
Strategic/Commercial |  |  | S
Financial/Economic/Market |  |  | F
Legal and Regulatory |  |  | L
Organisational/Management/Human Factors |  |  | O
Political |  |  | P
Environmental |  |  | E
Technical/Operational/Infrastructure |  |  | T
No | Date last reviewed | Risk description | Category | Owner (Accountable) | Manager (Responsible) | Inherent Risk |  |  | Measures in place to Manage the Risk | Residual risk |  |  | Financial Impact £k | Further action | Status | Comments on Status | Target Closure Date
a | c | d |  | e | f | Impact | Likelihood | Exposure | j | Impact | Likelihood | Exposure | (Estimated) | p | o
1 | 2010-01-01 | Funding applications to other organisations is rejected, risk of project being unable to proceed | S |  |  | Med | Low | Low |  | Low | Low | Low |  |  | New |  | 2010-01-01
3 | 2008-04-01 | Trade Union disruption |  | SRO | PM | low | low | Low
2 | 2010-01-01 | Funding applications to other organisations is delayed, risk of project not proceeding or delay | S |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
3 | 2010-01-01 | Funding applications to other organisations is less than anticipated, risk of project not proceeding or scope being reduced | S |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
5 | 2008-04-01 | TUPE |  | SRO |  | med | med | Med
4 | 2010-01-01 | Funding Appeal to raise balance of funding falls short or decision is delayed, risk of project not proceeding or scope being reduced | S |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
7 | 2008-04-01 | Mobilisation period problematic. Outgoing contractor un co operative/lacks resource, incoming contractor lacks resource:data transfer issues |  | SRO | PM | med | med | Med | Rigorous monitoring regime in place by client team and Technical Assurance. Establishment of migration plan, exit and mobilisation strategies in place | Med | Med | Med
8 | 2008-04-01 | Change in customer requirements |  | SRO | Project Board | med | med | Med
9 | 2008-04-01 | Non committed stakeholders |  | SRO | Project Board | med | med | Med
10 | 2008-04-01 | slow/inadequate stakeholder/user feedback in design process |  | SRO | Project Board | med | high | High
14 | 2008-04-01 | Bidding/Dialogue process not concluded in due time |  | SRO | PM | med | Med | Med | Tight control of dialogue process needed. Restrict meetings and areas for dialogue to key issues (KPIS/Pricing/incentivisation). Possible need to extend existing contract on rolling or short term basis | Med | Low | Low
5 | 2010-01-01 | Onerous conditions attached to grant applications causes delay/rejection, risk of project not proceeding | S |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
6 | 2010-01-01 | Sport England funding application is rejected/delayed/less than anticipated, risk of project not proceeding or scope being reduced | S |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
7 | 2010-01-01 | Cash flow less than anticipated target, resultant loss of some funding. Risk of delay, scope reduction, additional costs | S |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
8 | 2010-01-01 | Lack of strategic vision, are stakeholders/board members committed to partnership, do conflicts of interest exist? missed opportunities, delay, decision making process compromised, additional cost. | S |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
9 | 2010-01-01 | Suppliers encountering financial difficulties, potential delay, additional cost, legal issues. | S |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
10 | 2010-01-01 | Fraud/theft, miss appropriation of funds, risk of reputational damage, possible legal action, breach of grant conditions | S |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
11 | 2010-01-01 | Partnerships failing to deliver the desired outcomes. Operational difficulties, conflict with funders, risk of funding claw back, Project does not fulfil intended purpose | S |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
12 | 2010-01-01 | Completed project does not meet user/stakeholders partners expectations. Operational difficulties, conflict with funders, risk of funding claw back, Project does not fulfil intended purpose | S |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
13 | 2010-01-01 | Delays in site purchase. Risk of programme delay and extra cost. | S |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
14 | 2010-01-01 | Exchange rate fluctuations, potential to affect cost in planning stages, possible delay in construction phase. | F |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
15 | 2010-01-01 | Lack of liquidity in financial markets causes difficulty in raising loan finance or higher financing charges. Risk of additional cost and delay. | F |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
16 | 2010-01-01 | Interest rate instability, Risk of additional cost and delay. | F |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
17 | 2010-01-01 | Inflation . Risk of rising project costs, budget inadequate, tenders exceed budget, potential cost savings needed. Project delayed | F |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
18 | 2010-01-01 | Failure to meet projected revenue targets, risk of funding shortfall, risk of sinking fund shortfall, compromise on long term maintenance cost | F |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
19 | 2010-01-01 | Cost of project increases. Risk of scope creep, post contract variation, potential for delay and additional cost. | F |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
20 | 2010-01-01 | Tender prices exceed funding. Funding shortfall, need to reduce scope of project, time, cost and quality issues. | F |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
21 | 2010-01-01 | Cost of project increases during construction phase. Potential funding shortfall, need to reduce scope of project, time, cost and quality issues. | F |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
22 | 2010-01-01 | Delays in receipt of funding, resultant cashflow problems/inability to pay suppliers | F |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
23 | 2010-01-01 | Inadequate sinking fund provision/ inability to demonstrate provision. Potential funding rejection/delay | F |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
24 | 2010-01-01 | Inappropriate consideration of risks, inadequate financial provision for risk. Risk of insufficient budget/additional cost/programme delay/quality compromised/scope reduced | F |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
25 | 2010-01-01 | Business Plan objectives not met, or performance outcomes not achieved. Risk of funding claw back | L |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
26 | 2010-01-01 | Failure to monitor or meet KPIs. Risk of funding claw back | L |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
27 | 2010-01-01 | Breach of terms and conditions of funding agreements. Risk of funding claw back/funding shortfall, project delay. | L |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
28 | 2010-01-01 | Failure to comply with non project related legislation, H&S, Employment, Child protection etc. | L |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
29 | 2010-01-01 | Project related Public Liability claims against applicant. Risk of project delay and legal costs. | L |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
30 | 2010-01-01 | Possible need to comply with EU procurement requirements (OJEU), programme issues, additional consultancy costs. | L |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
31 | 2010-01-01 | OJEU alcatel challenge received during standstill period. Significant programme delay or Project may not proceed. Potential for additional legal and consultancy costs. | L |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
32 | 2010-01-01 | Failure to comply with EU remedies directive, alcatel challenge. Significant programme delay or Project may not proceed. Potential for additional legal and consultancy costs. | L |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
21 | 2008-04-01 | Disputes/claims with out going contractor |  | SRO | PM/PPT/Legal | med | High | High |  | Med | Med | Med
22 | 2008-04-01 | Best value tender significantly above PTE |  | SRO | Project Board | low | Med | Low |  | Low | Med | Low
33 | 2010-01-01 | Successful alcatel challenge. Significant programme delay or Project may not proceed. Potential for additional legal and consultancy costs. | L |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
34 | 2010-01-01 | Changes in regulatory or legislative requirements affect design, procurement or costs. | L |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
35 | 2010-01-01 | Change in rate of vat or other taxation issues | L |  |  | High | Med | High |  | High | Low | Med |  |  | New |  | 2010-01-01
36 | 2010-01-01 | Non compliance with Building Regulations. Risk of additional consultancy fees, programme and quality issues. | L |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
37 | 2010-01-01 | Inadequate Communications/lack of communications plan. Failure to communicate key works and implications/reputational damage with staff/stakeholders/partners. Lack of clarity in decision making process, programme delay, potential cost and quality issues. | O |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
38 | 2010-01-01 | Not all key stakeholders involved in decision making process, resultant conflict in requirements, programme delay, potential cost and quality issues. | O |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
39 | 2010-01-01 | Lack of employer resources, impact on decision making process, programme delay, potential cost and quality issues. | O |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
40 | 2010-01-01 | Issues not logged and actioned. Risk of change control not being actioned, additional consultancy and contractor costs, potential delay. | O |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
41 | 2010-01-01 | Loss of key staff/advisors, lack of continuity/skill gaps. Risk of project delay, inadequate communications, potential additional consultancy and contractor costs | O |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
42 | 2010-01-01 | Key personnel lack relevant skills, commitment and experience to undertake project. Risk of project delay, poor project management, additional contractor costs | O |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
43 | 2010-01-01 | Adverse impact on users of other adjacent facilities, fall in use of other facilities, complaints from users. Loss of revenue, need to revise site management/access arrangements, potential delay and additional project costs. | O |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
44 | 2010-01-01 | Machinery of Government Changes. Change of Gov. policy/organisation/change of government. | P |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
45 | 2010-01-01 | Adverse Publicity/media intervention. Potential for project delay, project put on hold, abortive costs incurred. | P |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
46 | 2010-01-01 | Fire, flood, wind damage during construction phase. Risk of delay/investigation, remedial works cost, additional consultancy fees | E |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
47 | 2010-01-01 | Inadequate planning/consideration of Environmental/Ecological and Waste issues. Risk of delay, investigations/tests and additional cost | E |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
48 | 2010-01-01 | Failure to deliver energy efficiency targets prescribed by brief/stakeholders/funders. Risk of funding claw back, addition fees incurred for remedial work design and works cost. | E |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
49 | 2010-01-01 | Failure to comply with sustainability policies in accordance with brief/stakeholders/funders conditions/requirements. Risk of funding rejection, project aborted, additional costs in redesign, works costs. | E |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
50 | 2010-01-01 | Planning approval expires or is renewed subject to onerous conditions. Risk of significant project delay or project cancelled. Additional design & quality issues and associated costs. | T |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
51 | 2010-01-01 | New planning approval required during construction phase due to variation in design. Risk of significant project delay and associated contractor costs. Additional design and associated costs. | T |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
52 | 2010-01-01 | Planning permission not granted/onerous conditions attached to Planning. Risk of significant project delay or project cancelled. Additional design & quality issues and associated costs. | T |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
53 | 2010-01-01 | Failure to comply with funders Technical Guidance/conflict between funders technical requirements. Risk of funding being withdrawn or reduced, potential additional cost/abortive design costs, stakeholder conflicts, programme delay. | T |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
54 | 2010-01-01 | Difficulties in meeting Project Monitors requirements/conflicts between different PMs requirements. Risk of funding being withdrawn or reduced, potential additional cost/abortive design costs, stakeholder conflicts, programme delay. | T |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
55 | 2010-01-01 | Conflict between Building Regulations relaxation/Funders Technical Requirements. Risk of funding being withdrawn or reduced, potential additional cost/abortive design costs, stakeholder conflicts, programme delay. | T |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
56 | 2010-01-01 | Impact of adjoining land owners requirements/covenants/party wall issues. Substantial risk of project delay with consequential additional costs. Risk of project cancellation | T |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
57 | 2010-01-01 | Utilities requirements. Water, Gas, Electricity. Cost uncertainty due to location of services, potential need for new mains, ground conditions and limited market. | T |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
58 | 2010-01-01 | Adverse ground conditions/onerous requirements from soil reports, potential effect on sub structure and below ground services design. Risk of additional cost for more robust substructure design. | T |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
59 | 2010-01-01 | Discovery of unknown below ground services post contract, additional design and cost, potential delay. | T |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
60 | 2010-01-01 | Archaeological requirements. Risk of extended precontract site investigation and cost, potential extended programme to accommodate investigations, potential project cancellation | T |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
61 | 2010-01-01 | Detailed design at variance with initial cost planning assumptions. Risk of additional project cost, potential programme implications. | T |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
62 | 2010-01-01 | Impact of un co ordinated detailed design. Risk of additional pre and construction phase cost , quality issues & unstructured change control, potential programme delay. | T |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
63 | 2010-01-01 | Soil conditions found to be at variance from soil report information. Risk of delay on substructure work with consequential additional design and contractor cost. | T |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
64 | 2010-01-01 | Asbestos/land contamination uncovered, need for remediation works. Risk of additional cost for remediation work and programme implications. | T |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
65 | 2010-01-01 | Project fails to meet business need/stakeholder requirements. Risk of funding claw back post completion, potential for additional work and associated cost. Operational limitations. | T |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
66 | 2010-01-01 | Changes to brief by Employer leading to design variations/possible delay. Risk of additional construction phase cost , quality issues & unstructured change control, potential programme delay. | T |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
67 | 2010-01-01 | Overall slippage in programme, risk of time delay and additional cost | T |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
68 | 2010-01-01 | Construction Phase Traffic Management, risk of danger to construction workers and site visitors, potential delay | T |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
69 | 2010-01-01 | Compliance with Disability Discrimination Act/Part M Building Regulations/Design Guidance Note. Inappropriate design consideration, post contract variation, potential additional cost and delay | T |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
70 | 2010-01-01 | Shortage of Construction Labour, potential for delay and substandard quality | T |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
71 | 2010-01-01 | Supply chain failure, sub contractor insolvency, risk of delay and quality compromised | T |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
72 | 2010-01-01 | Poor Contractor Performance, time/quality control issues, potential for delay, predicted cashflow not met, full funding not realised due to financial year spend conditions | T |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
73 | 2010-01-01 | Changes to agreed brief, design variation, contractor claims for loss and expense/compensation events, programme delay | T |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
74 | 2010-01-01 | Longer than expected lead in time for materials (specialist plant, steelwork etc.), potential for delay | T |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
75 | 2010-01-01 | Break ins/theft from site/vandalism. Increased construction site security. | T |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
76 | 2010-01-01 | Exceptional adverse weather conditions, potential for delay | T |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
77 | 2010-01-01 | Insufficient as built/building records/O&M/H&S files available. Additional costs/potential programme delay due to findings of Contractor verification. | T |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
78 | 2010-01-01 | Insufficient FM/Operators input and support to design results in in failure to obtain optimum design solution. Excessive change control, additional costs | T |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
79 | 2010-01-01 | Poor communications between Project Manager/design team and FM/Operator. Potential delay, access and security issues, additional cost | T |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
80 | 2010-01-01 | H&S risks due to lack of co ordination between FM and Project Manager/Contractor. Operational difficulties, revised working arrangements, potential delay and associated cost | T |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
81 | 2010-01-01 | Does comprehensive business plan and annual budget exist? Lack of strategic clarity, unrealistic expectations, sinking fund commitment not met, risk of funding claw back. | S/F |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
82 | 2010-01-01 | Extended recession/weak economy/down turn in demand. Down turn in demand for use of facility, income shortfall. | S/F |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
83 | 2010-01-01 | Rapid economic growth/rising tender prices/skills shortage. Market fluctuations, rising tender prices, budget shortfall, need for value engineering. | S/F |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
84 | 2010-01-01 | Supplier Insolvency (consultants/contractors). Project stopped, legal costs, significant additional cost, risk of cancellation. | S/F |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
85 | 2010-01-01 | Fluctuations in taxation. Insufficient funds, re design and downscaling. | F/P |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01
86 | 2010-01-01 | Major Accident on construction site, potential for delay and additional cost due to investigation and revised site management | T/L |  |  | Med | Med | Med |  | Med | Med | Med |  |  | New |  | 2010-01-01
87 | 2010-01-01 | Legislative changes affecting agreed design/brief, additional cost, potential for delay | T/L |  |  | Med | Med | Med |  | Low | Low | Low |  |  | New |  | 2010-01-01

## Closed risks
Sport England Generic Risk Register
Closed Risks Schedule
No | Date last reviewed | Risk description | Category | Owner | Manager | Inherent Risk |  |  | Measures in place to Manage the Risk | Residual risk |  |  | Financial Impact £k | Status | Comment on Status | Target Closure Date
a | c | d |  | e | f | Impact | Likelihood | Exposure | j | Impact | Likelihood | Exposure | (Estimated) | o | p

## Labels for boxes
High
Med
Low
New
Same
Better
Worse
Closed