## Risk log
Project name:
Project manager:
[Text in red and enclosed in [ ] is explanatory and should be deleted]
ID | Date raised | Risk description | Likelihood | Impact | Severity | Owner | Mitigating action | Contingent action | Progress on actions | Status
[1] | [12/12/2009] | [There is a risk that.... If this happens.....] | [High/Medium/Low] | [High/Medium/Low] | [High/Medium/Low. See Severity Table] | [Person managing the risk] | [Actions that can be taken to reduce the likelihood of the risk occuring. May also be acceptance of the risk or transferance of the risk e.g. insurance] | [What will be done if this risk does occur. Usually actions to reduce the impact on the project] | [Action taken and date. E.g. Update 13/12/2009 mitigation actions implemented] | [Open, Waiting, Closed]
[Notes
Every organisation has a different approach to the risk log. This example includes all of the information that needs to captured,
and has been used on numerous real world projects. However, feel free to tweak this to fit your project.]
[Columns you might want to add:
| Proximity | This indicates when the risk may occur and can be used to schedule risk mitigation activities.
| Raised by | Who identified the risk.
| Closed date | The date the risk was closed.
| Last update | The date that the risk entry was last updated. Useful for ensuring that mitigating actions are put in place.
| Action by | I have often seen this field used to differentiate between the person accountable for managing this risk and the person
actually carrying out any mitigating actions.]

## Severity Table
Likelihood
|  | 1 | 2 | 3
Impact | 1 | Low | Low | Medium
| 2 | Low | Medium | High
| 3 | Medium | High | High