## Risk Management Register
Status |  | Risk Type | Response Strategy |  | Construction | Cost |  | Exploit
Active |  | Threat | Avoid |  | Design | Time |  | Share
Dormant |  | Opportunity | Transfer |  | Environment | Scope |  | Enhance
Retired |  |  | Mitigate |  | External | Quality |  | Accept
|  |  | Accept |  | Organization
Project Management
Right of Way
Sample Risk Management Register for Project XXXX
Risk Identification | [8 empty] | Qualitative Risk Assessment | [8 empty] | Risk Response Plan |  | Monitoring and Control
# | RMP No. | Status | Risk Category | Risk Event | Cause | Effect | Threat or Opportunity | Primary Objective | Probability | Impact | Risk Matrix | [6 empty] | Response Strategy | Response Actions | Responsibile Entity | Interval or Milestone Check | Status: Date and Review Comments
1 |  | Active | External | Project not fully funded | Budget Constraints- allocation in doubt or subject to change | Project delayed | Threat | Time | High | Very High | Probability | VH | [5 empty] | Mitigate | Project may be divided into 2or 3 phases with options in the contract | Progam Engineer | Monthly | xx/xx/2008
[12 empty] | H |  |  |  |  | X
M
L
VL
[13 empty] | VL | L | M | H | VH
Impact
2 |  | Active | Design | Inaccurate cost estimate | Unit pricing effected by rock excavation and disposal site issues | EE is underestimated | Threat | Cost | Medium | Medium | Probability | VH | [5 empty] | Mitigate | Increased unit price for excavation to match rock excavation price | Geotechnical Manager | At completion of subsurface exploration | xx/xx/2008
H
[12 empty] | M |  |  | X
L
VL
[13 empty] | VL | L | M | H | VH
Impact
3 |  | Active | Construction | Unidentified utility impacts | Unidentified utilities | Project cost increases | Threat | Cost | Low | Low | Probability | VH | [5 empty] | Transfer | Contingency plan. Contractor is responsible for coordination. | Utility Engineer | Monthly | xx/xx/2008
H
M
[12 empty] | L |  | X
VL
[13 empty] | VL | L | M | H | VH
Impact
4 |  | Active | External | Permit delays | Permits expire. Permits or agency actions are delayed or take longer then expected. | Fines, penalties and project delays | Threat | Time | Medium | Low | Probability | VH | [5 empty] | Transfer | Consultant reponsible for coordinating permits and identifying permit requirements. | Environmental Engineer | Monthly | xx/xx/2008
H
[12 empty] | M |  | X
L
VL
[13 empty] | VL | L | M | H | VH
Impact
5 |  | Active | Construction | Differing site conditions | Unexpected geotechnical issues. Natural or manmade obstructions. | Increased project costs | Threat | Cost | Medium | Medium | Probability | VH | [5 empty] | Mitigate | Thorough geotechnical investigations performed | Geotechnical Engineer | At completion of subsurface exploration | xx/xx/2008
H
[12 empty] | M |  |  | X
L
VL
[13 empty] | VL | L | M | H | VH
Impact
6 |  | Active | Project Management | Marketing opportunities | Public exposure of a high profile FLH project | Improves viability of FLH | Opportunity | Quality | High | High | Probability | VH | [5 empty] | Exploit | Future marketing of this successful project by the Division | Project Manager | Monthly | xx/xx/2008
[12 empty] | H |  |  |  | X
M
L
VL
[13 empty] | VL | L | M | H | VH
Impact
[11 empty] | Probability | VH
H
M
L
VL
[13 empty] | VL | L | M | H | VH
Impact
Note on J11: See Risk Ranking
Note on K11: See Risk Ranking
Note on T11: For examples see: www.cflhd.gov/Project_Management/Documents/PPIGuidelines/TEMPLATES/Risk_Assessment_Questionnaire_template.doc
Note on U11: Enter Entity: EFL, VDOT, Design-Builder, etc.

## Sample Risk Events
Sample Risk Events*
Design/Construction Project Sample Risk List
Construction Risks
Unidentified utility impacts
Unexpected archeological findings
Changes during construction not in contract
Unidentified hazardous waste
Site is unsafe for workers
Delays due to traffic management and lane closures
Design Risks
Incomplete quantity estimates
Insufficient design analysis
Complex hydraulic features
Surveys incomplete
Inaccurate assumptions during the planning phase
Environmental Risks
Unanticipated noise impacts
Unforeseen Section 4(f) resources affected
Environmental clearance for borrow site required
Unanticiapated barriers to wildlife
Unforeseen air quality issues
External Risks
Project not fully funded
Politically driven accelerated schedule
Permit agency actions cause unexpected delays
Public objections
Inflation and other market forces
Organizational Risks
Resource conflicts with other projects
Inexperienced staff assigned to project
Lack of specialized staff
Approval and decision processes cause delays
Priorities change on existing programs
Project Management Risks
Inadequate project scoping and scope creep
Consultant and contractor delays
Estimating and/or scheduling errors
Lack of coordination and communication
Unforeseen agreements required
Right of Way Risks
Unanicipated escalation in ROW values
Additional ROW may be needed
Acquisition of ROW may take longer than anticipated
Discovery of hazardous waste during the ROW phase
Generic Project Sample Risk List
Technical, Quality, or Performance Risks
Examples include reliance on unproven or complex technolgy, unrealistic performance goals, long term performance, process roadblocks, new emerging initiatives, increases in complexity, etc..
External Risks
Examples include a shifting regulatory environment, labor issues, changing customer priorities, government agency risks, and weather. Also to be considered are consultant and vendor contract risks, contract type and contractor responsibilities.
Organizational Risks
Examples include lack of prioritization of projects, inadequacy or interruption of funding, inexperienced and poorly developed and trained workforce, and resource conflicts with other projects in the organization.
Project Management Risks
Examples include poor allocation of time and resources, inadequate quality of the project plan, lack of project manager delegated authority, and lack of project management disciplines.
* When identifying risk it is important to specify the risk correctly. As a guideline for identifying risk, use the following risk statement structure to help fill in the appropriate risk columns on the risk register: "Because of the cause or condition that is true, a risk event may occur, having an effect on either a cost, quality, scope or time objective."